## Instructions
Sheet | Purpose
Accounts | Account owners, delivery units, client contacts, and monthly targets
Projects | Raw revenue, trend, forecast, and billing ownership inputs
Billing Milestones | Milestone completion and billing trigger records
Collections | Invoice and collection tracking records
Thresholds | Agent-specific dynamic risk thresholds editable from the UI

## Accounts
Account Name | Industry | Delivery Unit | Account Manager | Account Manager Email | Client Contact Name | Client Contact Email | Account Monthly Target | Contract Value
PepsiCo | Consumer Goods | Data & AI | Priya Sharma | priya.sharma@bfmdemo.local | Daniel Cooper | daniel.cooper@pepsico-demo.local | 2400000 | 6000000
Comcast | Telecom | Digital Engineering | Neha Iyer | neha.iyer@bfmdemo.local | Melissa Grant | melissa.grant@comcast-demo.local | 1650000 | 5100000
HSBC | Banking | Managed Services | Rohit Desai | rohit.desai@bfmdemo.local | Liam Porter | liam.porter@hsbc-demo.local | 1500000 | 4750000
AstraZeneca | Life Sciences | Enterprise Platforms | Kavya Nair | kavya.nair@bfmdemo.local | Sophia Reed | sophia.reed@astrazeneca-demo.local | 1700000 | 5500000
Cisco | Networking | Cyber Defense | Sanjay Patel | sanjay.patel@bfmdemo.local | Victor Hill | victor.hill@cisco-demo.local | 1450000 | 4550000
Target | Retail | Commerce Platforms | Ananya Rao | ananya.rao@bfmdemo.local | Grace Miller | grace.miller@target-demo.local | 780000 | 2300000

## Projects
Account Name | Project Code | Project Name | Service Line | Billing Type | Billing Owner | Billing Owner Email | Contract Value | Revenue Plan (Month) | Revenue Plan (Quarter) | Revenue Recognized | Recognized Last 7 Days | Recognized Last 30 Days | Pending Pipeline | Forecast Bias | Last Revenue Update | Billing Cycle Days | Start Date | End Date
PepsiCo | PRJ-4456 | Global Data Platform Rollout | Data Modernization | Milestone | Aditya Bose | aditya.bose@bfmdemo.local | 3600000 | 1400000 | 4200000 | 1100000 | 35000 | 140000 | 30000 | 0.95 | 2026-03-11 | 7 | 2025-05-01 | 2027-05-11
PepsiCo | PRJ-4521 | Retail Insights Factory | Analytics Engineering | Time & Material | Meera Jain | meera.jain@bfmdemo.local | 2400000 | 1000000 | 3000000 | 800000 | 25000 | 108000 | 10000 | 0.88 | 2026-03-14 | 14 | 2025-06-30 | 2027-03-12
Comcast | PRJ-4588 | Customer App Modernization | Digital Product Engineering | Milestone | Kiran Sethi | kiran.sethi@bfmdemo.local | 2900000 | 900000 | 2700000 | 690000 | 40000 | 155000 | 80000 | 1.02 | 2026-03-13 | 10 | 2025-05-31 | 2027-04-21
Comcast | PRJ-4620 | Network AIOps Pilot | Platform Engineering | Time & Material | Rashmi Gupta | rashmi.gupta@bfmdemo.local | 2200000 | 750000 | 2250000 | 580000 | 28000 | 118000 | 45000 | 0.98 | 2026-03-12 | 14 | 2025-09-18 | 2027-02-10
HSBC | PRJ-4711 | Regulatory Data Platform | Data Platforms | Milestone | Nikhil Verma | nikhil.verma@bfmdemo.local | 2700000 | 850000 | 2550000 | 780000 | 25000 | 100000 | 35000 | 1.03 | 2026-03-15 | 7 | 2025-05-11 | 2027-05-11
HSBC | PRJ-4730 | Treasury Operations Support | Finance Ops | Time & Material | Asha Menon | asha.menon@bfmdemo.local | 2050000 | 650000 | 1950000 | 590000 | 18000 | 88000 | 20000 | 1 | 2026-03-15 | 14 | 2025-07-20 | 2027-04-11
AstraZeneca | PRJ-4870 | SAP Finance Transformation | ERP Modernization | Milestone | Ritu Chopra | ritu.chopra@bfmdemo.local | 3100000 | 980000 | 2940000 | 720000 | 30000 | 128000 | 55000 | 0.9 | 2026-03-09 | 7 | 2025-04-21 | 2027-07-10
AstraZeneca | PRJ-4902 | Clinical Data Lake | Data Platforms | Time & Material | Naveen Pillai | naveen.pillai@bfmdemo.local | 2400000 | 720000 | 2160000 | 530000 | 20000 | 86000 | 60000 | 0.88 | 2026-03-10 | 10 | 2025-07-20 | 2027-04-21
Cisco | PRJ-5031 | SOC Automation Program | Cybersecurity | Milestone | Harsh Bhatia | harsh.bhatia@bfmdemo.local | 2500000 | 830000 | 2490000 | 810000 | 18000 | 82000 | 20000 | 1.05 | 2026-03-16 | 7 | 2025-06-10 | 2027-03-12
Cisco | PRJ-5077 | Secure Network Reliability | Network Engineering | Time & Material | Tanya Singh | tanya.singh@bfmdemo.local | 2050000 | 620000 | 1860000 | 600000 | 15000 | 70000 | 10000 | 1.02 | 2026-03-15 | 14 | 2025-08-09 | 2027-02-10
Target | PRJ-5105 | Store Commerce Engine | Commerce Engineering | Milestone | Varun Kapoor | varun.kapoor@bfmdemo.local | 2300000 | 780000 | 2340000 | 745000 | 20000 | 92000 | 15000 | 1 | 2026-03-16 | 7 | 2025-07-10 | 2027-03-12
Comcast | PRJ-6120 | Billing Modernization Sprint | Digital Engineering | Milestone | Ravi Kumar | ravi.kumar@bfmdemo.local | 1800000 | 450000 | 1350000 | 280000 | 45000 | 180000 | 220000 | 1.05 | 2026-03-11 | 30 | 2025-11-17 | 2026-07-15
Target | PRJ-6399 | Omnichannel Analytics Upgrade | Commerce Platforms | Fixed Price | Maya Singh | maya.singh@bfmdemo.local | 2400000 | 600000 | 1800000 | 410000 | 60000 | 260000 | 300000 | 0.95 | 2026-03-14 | 45 | 2025-10-18 | 2026-08-14

## Billing Milestones
Project Code | Milestone Name | Completion Date | Billable Amount | Billed Amount | Invoice Generated | Invoice Number | Invoice Date | Account Manager Response | Status Note
PRJ-4456 | Wave 3 billing package | 2026-03-07 | 220000 | 0 | No |  |  | Pending | Revenue recognized but invoice trigger is pending.
PRJ-4456 | Data migration sign-off | 2026-03-10 | 200000 | 0 | No |  |  | Pending | Awaiting account manager approval to release invoice.
PRJ-4521 | Sprint 18 billing lot | 2026-03-13 | 70000 | 50000 | Yes | INV-4521-88 | 2026-03-15 | Pending | Partially invoiced while change order is being approved.
PRJ-4588 | Release train 7 sign-off | 2026-03-09 | 180000 | 120000 | Yes | INV-4588-17 | 2026-03-14 | Pending | Residual services effort is pending billing release.
PRJ-4620 | Observability milestone | 2026-03-11 | 95000 | 40000 | Yes | INV-4620-41 | 2026-03-13 | Pending | Invoice created but not fully billed against completed effort.
PRJ-4711 | Regulatory release billing | 2026-03-15 | 110000 | 110000 | Yes | INV-4711-22 | 2026-03-16 | Completed | Billing released on schedule.
PRJ-4730 | Treasury operations monthly pack | 2026-03-12 | 85000 | 70000 | Yes | INV-4730-11 | 2026-03-14 | Pending | Variance pending customer acceptance.
PRJ-4870 | ERP wave 3 milestone | 2026-03-05 | 210000 | 60000 | Yes | INV-4870-18 | 2026-03-09 | Pending | Large billing hold due to sign-off delay.
PRJ-4902 | Clinical ingestion baseline | 2026-03-08 | 140000 | 35000 | Yes | INV-4902-04 | 2026-03-10 | Pending | Billing lag is impacting revenue realization.
PRJ-5031 | Security automation release | 2026-03-16 | 75000 | 75000 | Yes | INV-5031-31 | 2026-03-16 | Completed | Current cycle billing completed.
PRJ-5077 | Reliability squad monthly billing | 2026-03-14 | 65000 | 58000 | Yes | INV-5077-09 | 2026-03-15 | Pending | Minor pending effort remains to be billed.
PRJ-5105 | Commerce engine go-live | 2026-03-15 | 90000 | 90000 | Yes | INV-5105-02 | 2026-03-16 | Completed | Milestone billed on time.
PRJ-6120 | Data pipeline milestone | 2026-03-10 | 180000 | 0 | No |  |  | Pending
PRJ-6399 | Reporting rollout | 2026-03-05 | 240000 | 120000 | Yes | INV-5521 | 2026-03-12 | In Progress

## Collections
Project Code | Invoice Number | Invoice Amount | Amount Received | Invoice Date | Due Date | Collected Date | Client Response Status | Status Note
PRJ-4456 | INV-4410 | 460000 | 460000 | 2026-01-06 | 2026-02-05 | 2026-02-07 | Completed | Payment collected within terms.
PRJ-4456 | INV-4482 | 220000 | 0 | 2026-01-14 | 2026-02-13 |  | Pending | Client has not responded to the last reminder.
PRJ-4521 | INV-4521-61 | 730000 | 640000 | 2026-02-17 | 2026-03-19 | 2026-03-11 | Promised | Client committed to clear balance next week.
PRJ-4588 | INV-4588-12 | 540000 | 410000 | 2026-01-31 | 2026-03-02 | 2026-03-07 | Pending | Balance is still pending on approved invoice.
PRJ-4620 | INV-4620-18 | 515000 | 360000 | 2026-02-09 | 2026-03-11 | 2026-03-09 | Promised | Part-payment received, rest pending approval.
PRJ-4711 | INV-4711-10 | 720000 | 720000 | 2026-02-21 | 2026-03-23 | 2026-03-13 | Completed | Collected in full.
PRJ-4730 | INV-4730-08 | 535000 | 470000 | 2026-02-12 | 2026-03-14 | 2026-03-08 | Promised | Client confirmed payment processing.
PRJ-4870 | INV-4870-01 | 430000 | 180000 | 2026-01-24 | 2026-02-23 | 2026-03-03 | Pending | Collections follow-up is ongoing.
PRJ-4902 | INV-4902-07 | 325000 | 140000 | 2026-02-06 | 2026-03-08 | 2026-03-06 | Pending | Client disputes a milestone amount.
PRJ-5031 | INV-5031-04 | 790000 | 790000 | 2026-02-24 | 2026-03-26 | 2026-03-12 | Completed | Collected in full.
PRJ-5077 | INV-5077-16 | 585000 | 540000 | 2026-02-19 | 2026-03-21 | 2026-03-10 | Promised | Balance expected this cycle.
PRJ-5105 | INV-5105-12 | 740000 | 740000 | 2026-02-27 | 2026-03-29 | 2026-03-13 | Completed | Invoice closed.
PRJ-6120 | INV-5520 | 150000 | 0 | 2026-02-05 | 2026-03-07 |  | Pending
PRJ-6399 | INV-5521 | 120000 | 60000 | 2026-02-25 | 2026-03-27 |  | Partial

## Thresholds
Agent Key | Metric Key | Label | Unit | Medium Value | High Value | Description
revenue_realization | forecast_shortfall_ratio | Revenue shortfall ratio | percent | 0.05 | 0.12 | Gap between forecast and target used for revenue realization risk.
revenue_realization | revenue_delay_days | Revenue update delay | days | 4 | 8 | Days since the last revenue recognition update.
billing_trigger | billing_delay_days | Billing delay | days | 4 | 7 | Days between milestone completion and billing trigger.
billing_trigger | unbilled_amount | Pending billable amount | currency | 100000 | 250000 | Unbilled milestone value that should already have triggered invoicing.
unbilled_revenue | days_unbilled | Unbilled aging | days | 5 | 10 | How long revenue has remained recognized but not billed.
unbilled_revenue | unbilled_amount | Unbilled revenue | currency | 120000 | 300000 | Revenue recognized but not yet invoiced.
collection_monitoring | overdue_days | Overdue days | days | 15 | 30 | Days an invoice remains overdue.
collection_monitoring | outstanding_balance | Outstanding balance | currency | 100000 | 200000 | Receivable value still open on the invoice.
revenue_forecasting | forecast_gap_ratio | Forecast gap ratio | percent | 0.05 | 0.12 | Forecasted shortfall versus target.